EVMS Test Metric Specification

Guideline No:

- 02

Test Metric ID:

02A101a

Test Type:

Manual

Attribute/Intent Definition:

02A1:  A single  organizational structure exists that contains all of the organizational elements, including major subcontractors and inter-organizational units, necessary to execute the contract

Test Definition:

Is there a single OBS used on the contract?

Test Metric:

X = Count of mismatches between the program organizational breakdown structure (OBS) and IPMR/CPR Format 2 or IPMDAR CPD

Metric Threshold:

X=0

Data Elements Required:

07 Organization Breakdown Structure

07A OBS elements

20 IPMR/CPR/IPMDAR

20Q Format 2 OBS elements/ CPD OBS

Assumptions:

- There is a corresponding relationship between the program organizational chart and OBS.

Instructions:

- Compare IPMR/CPR Format 2 or IPMDAR CPD OBS to the program OBS (organizational chart). Verify all elements required in the Format 2, Block 5(a) or CPD OBS are contained in the OBS.  Verify all elements in the reporting level of the OBS are in Format 2 or CPD OBS.

- Count the number of missing/incorrect organizational elements identified in Step 1. This is the value (X) of the test metric.

- If there are no missing/incorrect OBS elements (X=0), then the metric is not out of threshold.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 7/19/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 08/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 6, 8, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |