EVMS Test Metric Specification

Guideline No:

- 03

Test Metric ID:

03A101a

Test Type:

Manual

Attribute/Intent Definition:

03A1:  The planning, scheduling, budgeting, work authorization and cost accumulation systems are integrated  via a common coding structure and, as appropriate, with the Contract Work Breakdown Structure (CWBS) and the  organizational structure at the  Control Account (at a minimum) through the total contract level.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Do baseline dates align between the work authorization documentation (WAD) and IMS? (count)

Test Metric:

X = Count of sampled incomplete CAs with IMS baseline dates outside the WAD POP

Y = Total count of  incomplete CAs in IMS that were sampled

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

09 Work Authorization Documentation (WAD)

09C Baseline Finish Date

09D Baseline Start Date

11 Integrated Master Schedule (IMS)

11A Actual Finish Date

11G Baseline Finish Date

11J Baseline Start Date

45 IMS Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete CAs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Incomplete CA equals at least one task/activity or milestone without an actual finish date in the IMS.

Instructions:

- Identify a sample of incomplete CAs in the IMS; this is the denominator (Y) of the metric.

- Identify the baseline start and baseline finish dates in the WADs for the sampled CAs.

- Compare the baseline start and the baseline finish dates for each incomplete CA between the WAD and the IMS.

- Count each instance where at least one of the baseline dates (baseline start, baseline finish, or both) is outside the WAD POP in the IMS; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB – validated |  | 4/20/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | Minor changes |  | 3/23/2017 |
| v.3.1 | Minor changes, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.2 | Updated Data Elements with EV Cost Tool Data, updated assumptions |  | 2/21/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v.3.6.1 | Re-defined Incomplete CA in block 11 |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |