EVMS Test Metric Specification

Guideline No:

- 03

Test Metric ID:

03A101e

Test Type:

Automated/Manual

Attribute/Intent Definition:

03A1:  The planning, scheduling, budgeting, work authorization and cost accumulation systems are integrated  via a common coding structure and, as appropriate, with the Contract Work Breakdown Structure (CWBS) and the  organizational structure at the  Control Account (at a minimum) through the total contract level.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Does discrete WP EV percent complete align between the IMS and EV Cost Tool?

Test Metric:

X = Count of discrete WPs in IMS where EV % complete does not match EV % complete in the EV Cost Tool data

Y = Total count of discrete WPs in the IMS

Metric Threshold:

X/Y = 0%

Data Elements Required:

11 Integrated Master Schedule

11T EV % complete

11U EVT

11AP WP/PP/SLPP UIDs

13 EV Cost Tool Data

13AN EV % complete

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- Differences due to rounding error by 1% in the EV% values are not considered a deficiency.

- If there are more than one IMS task associated with any single WP ID (many to one relationship), this metric may need to be a Manual metric (not Automated).

- PPs and SLPPs are excluded in the X and Y counts.

- The IMS status date should be aligned with Format 1 reporting month, as applicable. If the IMS Status Date does not match the Format 1 Period end date, this metric is out of threshold.

- This metric should only be evaluated where the contractor has an internal requirement for EV % complete in the IMS or the contractor uses the IMS to status the EV Cost Tool.

Instructions:

- Identify and count all discrete WPs in the IMS; this is the denominator (Y) of the metric.

- Compare the EV % complete values for each discrete WPs in the EV Cost Tool data with the WP EV % complete in the IMS, and count each instance where the values differ.  This is the numerator (X) of the metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 7/19/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Added discrete and updated assumptions, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | Update Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Admin update to add “data” after cost tool & capitalize “Cost Tool”. Removed Pass/Fail verbiage to allow assessment of test result without assuming an automatic pass or fail. Added data elements 44 & 45 to supplement artifacts 11 & 13. Replaced “discrepancy” for “deficiency” to be consistent with the overarching 2303-01. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |