EVMS Test Metric Specification

Guideline No:

- 03

Test Metric ID:

03A101h

Test Type:

Automated

Attribute/Intent Definition:

03A1:  The planning, scheduling, budgeting, work authorization and cost accumulation systems are integrated  via a common coding structure and, as appropriate, with the Contract Work Breakdown Structure (CWBS) and the  organizational structure at the  Control Account (at a minimum) through the total contract level.

Test Definition:

Is control account data traceable between the system artifacts including schedule, cost data, and work authorization documents?

- Does the OBS align between the IMS and EV Cost Tool?

Test Metric:

X = Count of incomplete CAs where IMS OBS does not match EV Cost Tool OBS, or there are more than one IMS OBS assigned, or no IMS OBS assigned.

Y = Total count of incomplete CAs in the IMS

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11AB OBS Elements

11AR CA UIDs

13 EV Cost Tool Data

13AA CA UIDs

13AS OBS Elements

44 Cost Data Dictionary

45 IMS Data Dictionary

59 RAM

59A CAM Assignment

Assumptions:

- If the IMS does not contain the OBS field, determine alternate method for conducting the test (e.g., CA to RAM trace).

- If the IMS contains the OBS field but the OBS element is not in the IMS, the incomplete CA counts as a trip even if the EV Cost Tool data has no OBS element assigned either.

- If the IMS contains the OBS field but the OBS element is not consistently applied in the IMS (i.e., some incomplete CA tasks/activities or milestones are populated and others are not), this counts as “more than one OBS element assigned” and the incomplete CA counts as a trip.

- All incomplete CAs that are in the IMS but not in the EV Cost Tool data trip this metric.

- All incomplete CAs that are in the IMS and have more than one OBS element assigned in the EV Cost Tool data trip this metric.

- Incomplete CA equals at least one task/activity or milestone without an actual finish date in the IMS.

Instructions:

- Identify and count all incomplete CAs in the IMS; this is the denominator (Y) of the test metric.

- For each incomplete CA, compare the OBS element assigned in the IMS to the OBS element assigned in the EV Cost Tool data or CA to RAM trace. Count each instance where the OBS elements do not match, or there are more than one IMS OBS assigned, or no IMS OBS assigned; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Minor change submitted to CCB |  | 2/28/2017 |
| v3.0 | Minor changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Minor Updates to Data Elements, Assumptions & Instructions |  | 2/21/2019 |
| v3.3 | Removed Data Elements, removed unnecessary Assumption & added incomplete Assumption |  | 5/24/2019 |
| v3.4 | Update: Attribute and Metric Threshold |  | 8/31/2019 |
| v3.5 | Update: Test Metric, Data Element Required, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v3.6.1 | Updated Incomplete CA definition in block 11. Added “data” in block 11. Admin changes to correct capitalization |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 for consistency & added data elements 44 & 45 to supplement artifacts 11 & 13. | 8 &10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |