EVMS Test Metric Specification

Guideline No:

- 03

Test Metric ID:

03A101i

Test Type:

Automated

Attribute/Intent Definition:

03A1:  The planning, scheduling, budgeting, work authorization and cost accumulation systems are integrated with each other via a common coding structure and, as appropriate, with the Contract Work Breakdown Structure (CWBS) and the Organizational Breakdown Structure (OBS) at Control Account (at a minimum) through the total contract level.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Does the WBS align between the IMS and EV Cost Tool?

Test Metric:

X = Count of incomplete CAs where IMS WBS does not match EV Cost Tool WBS, or there are more than one IMS WBS assigned, or no IMS WBS assigned.

Y = Total count of incomplete CAs in the IMS

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11AN WBS Elements

11AR CA UIDs

13 EV Cost Tool Data

13AA CA UIDs

13AZ WBS Elements

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- If the WBS element is not in the IMS, the incomplete CA counts as a trip even if the EV Cost Tool data has no WBS element assigned either.

- If the WBS element is not consistently applied in the IMS (i.e., some incomplete CA tasks/activities or milestones are populated and others are not), this counts as “more than one WBS element assigned” and the incomplete CA counts as a trip.

- All incomplete CAs that are in the IMS but not in the EV Cost Tool data trip this metric.

- All incomplete CAs that are in the IMS and have more than one WBS element assigned in the EV Cost Tool data trip this metric.

- Incomplete CA equals at least one task/activity or milestone without an actual finish date in the IMS

Instructions:

- Identify and count all incomplete CAs in the IMS; this is the denominator (Y) of the metric.

- For each incomplete CA, compare the WBS element in the IMS to the EV Cost Tool data.  Count each instance where the IMS WBS does not match the EV Cost Tool data WBS, or there are more than one IMS WBS assigned, or no IMS WBS assigned; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/6/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Added Actual Finish Date in Data Elements, added IMS incomplete assumption |  | 2/21/2019 |
| v3.3 | Removed Data Elements, removed unnecessary Assumption & added incomplete Assumption |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | Update: Test Metric, Data Elements Required, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v3.6.1 | Updated Incomplete CA definition in block 11. Added “data” in blocks 11 and 12 for consistency |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 for consistency & added data elements 44 & 45 to supplement artifacts 11 & 13. | 8 &10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |