EVMS Test Metric Specification

Guideline No:

- 03

Test Metric ID:

03A103a

Test Type:

Manual

Attribute/Intent Definition:

03A1:  The planning, scheduling, budgeting, work authorization and cost accumulation systems are integrated with each other via a common coding structure and, as appropriate, with the Contract Work Breakdown Structure (CWBS) and the Organizational Breakdown Structure (OBS) at Control Account (at a minimum) through the total contract level.

Test Definition:

Do the forecast start and finish dates in the subcontractor/supplier IMS reconcile to the prime IMS?

Test Metric:

X = Count of sampled incomplete tasks/activities & milestones in the subcontractor/supplier IMS with a forecast start/finish date that cannot be reconciled to the forecast start/finish date in the prime IMS

Y = Total count of sampled incomplete subcontractor/supplier tasks/activities & milestones in the prime contractor IMS

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

03 EVM System Description

11 Integrated Master Schedule (IMS)

11A Actual Finish Date

11V Forecast Finish Date

11W Forecast Start Date

11AH Subcontractor ID

11AM Task/Milestone UIDs

37 Subcontractor/Supplier Schedule

37C Forecast Finish Date

37D Forecast Start Date

37G Task/Milestone UIDs

45 IMS Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete tasks/activities & milestones.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Incomplete tasks/activities & milestones equals no actual finish date in the IMS.

- The count is performed at the task/activity & milestones level, and each task/activity & milestones can only count as a single trip.

Instructions:

- Filter the prime contractor IMS to identify a sample of incomplete subcontractor/supplier tasks/activities & milestones.  The count of these tasks/activities & milestones is the denominator (Y) of the test metric.

- At the level commensurate with the inclusion of subcontractor/supplier tasks/activities & milestones in the prime contractor IMS, review the forecast start and forecast finish dates for the corresponding subcontractor/supplier IMS elements for the tasks/activities & milestones identified.

- Review the prime contractor IMS to ensure that forecast start and forecast finish dates of corresponding tasks/activities & milestones from the subcontractor/supplier schedule can be reconciled.

- If a deficiency exists between subcontractor/supplier data and prime contractor data, document the number of tasks/activities & milestones with deficiencies.  This number is the numerator (X) in the test metric calculation.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/6/2015 |
| v2.0 | CCB - validated |  | 7/19/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | Minor changes |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v3.6.1 | Re-defined incomplete. Added “tasks” and “& milestones” in block 11 and 12. Updated data elements in block 10 for consistency | 10, 11, 12 | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11 & updated blk 10 to align with test requirements. Added “/supplier” (lower level IMS must support prime IMS) regardless of EVMS flow down. Replaced "discrepancy" for "deficiency" - to be consistent with the overarching 2303-01. Updated asm 3 blk 9 to align definition of IMS “incomplete” with DECM verbiage for consistency. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |