EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A101a

Test Type:

Automated

Attribute/Intent Definition:

06A1:  The IMS reflects all authorized, time-phased discrete work, including subcontracted effort and critical and high-value material.

Test Definition:

Does each non-LOE unique WP, PP, SLPP have task(s) represented in both the IMS and EV Cost Tool?

Test Metric:

X = Count of incomplete non-LOE WPs, PPs, SLPPs in the EV Cost Tool that are not in the IMS and count of incomplete non-LOE WPs, PPs, SLPPs in the IMS that are not in the EV Cost Tool

Y = Total count of all unique, incomplete, non-LOE WPs, PPs, and SLPPs in the EV Cost Tool or the IMS

Metric Threshold:

X/Y = 0%

Data Elements Required:

03 EVM System Description

03V Process for LOE/discrete work decomposition

03U Guidance on EVTs

11 Integrated Master Schedule

11A Actual Finish Date

11U EVT

11AG Status Date

11AP WP/PP/SLPP UIDs

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AP EVT

13BA WP/PP/SLPP UIDs

13BC Cost Data Status Date

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- Status date of EV Cost Tool data is aligned with IMS status date.

- Test Metric is performed with incomplete non-LOE WPs, all PPs (GL10 – Attribute 3), and all SLPPs (GL 8 – Attribute 1).

- If BAC and BCWPCUM are within $100 (or 1 hour), then WPs/PPs/SLPPs are complete.

- Review the contractor’s System Description and determine how the M/ERP managed scope is aggregated, with the appropriate interdependencies and sequencing preserved, within the IMS.

- Incomplete WP/PP/SLPP equals at least one task/activity or milestone without an actual finish date in the IMS.

- Review EVM System Description for what work is required to be in the IMS. If the system description is silent, only work with earned value techniques defined as non-discrete or LOE may be omitted from the IMS.

Instructions:

- Identify and count all incomplete Non-LOE WPs, PPs, SLPPs in the EV Cost Tool data.

- Compare the WP/PP/SLPP unique IDs of incomplete work in the EV Cost Tool with the IMS. Count each incomplete WP, PP, SLPP in the EV Cost Tool data that is not in the IMS.

- Identify and count all incomplete Non-LOE WP, PPs, SLPPs in the IMS.

- Compare the WP/PP/SLPP unique IDs of incomplete work in IMS with the EV Cost Tool data. Count each incomplete WP, PP, SLPP in the IMS that is not in the EV Cost Tool data.

- The Y Value is the sum the unique WP/PP/SLPPs in steps 1 and 3.

- The X Value is the sum of steps 2 and 4.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB – validated |  | 4/20/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | Minor changes |  | 3/23/2017 |
| v.3.1 | Minor changes, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.2 | Updated Data Elements with EV Cost Tool Data, updated assumptions |  | 2/21/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v.3.6.1 | Re-defined Incomplete CA in block 11 |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |