EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A102a

Test Type:

Manual

Attribute/Intent Definition:

06A1:  The IMS reflects all authorized, time-phased discrete work  including subcontracted effort and critical and high-value material

Test Definition:

Are authorized risk mitigation activities incorporated into the IMS as required by the process instructions?

Test Metric:

X = Count of risk mitigation activities not in the IMS

Y = Total count of risk mitigation activities

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

03 EVM System Description

11 Integrated Master Schedule

11E Approved Risk Mitigation Activities

28 Risk & Opportunities Log/Register

28A Approved Risk Mitigation Activities

45 IMS Data Dictionary

62 Risk Management Process/ Plan

Assumptions:

- None

Instructions:

- Identify and count the total number of approved risk mitigation activities that require incorporation into the IMS per the EVM system description, approved risk management plan, and/or risk mitigation process/procedure; this is the denominator (Y) of the test metric.

- Identify and count any approved risk mitigation activities that cannot be traced to the IMS; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Added Data Elements 03 and 62; updated assumptions from blank to “None” | 8, 9 | 10/27/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |