EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A210a

Test Type:

Automated/Manual

Attribute/Intent Definition:

06A2:  The network schedule/IMS depicts the sequence of work (horizontal integration) and identifies the significant interdependencies that are indicative of the actual way the work is planned and accomplished.

Test Definition:

Do LOE tasks/activities have discrete successors?

Test Metric:

X = Count of incomplete LOE tasks/activities in the IMS with at least one Non-LOE successor

Y = Total count of incomplete LOE tasks/activities in the IMS

Metric Threshold:

X/Y = 0%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11U EVT

11AJ Successors

45 IMS Data Dictionary

Assumptions:

- Incomplete LOE tasks/activities equals no actual finish date in the IMS.

- Incomplete LOE tasks/activities that have end item deliverables or contract completion as their only successors are not considered a deficiency.

- Successors that are not identified as LOE are included in the numerator count.

Instructions:

- Identify and count all incomplete LOE tasks/activities in the IMS; this is the denominator (Y) of the test metric.

- Identify and count any incomplete LOE tasks/activities with at least one Non-LOE successor (task/activity or milestone); this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Changed to Incomplete LOE and updated assumptions, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.2 | Added Assumption 3 |  | 2/21/2019 |
| v3.3 | Added Data Element, Updated “discrete” to “Non-LOE”, added Assumption 4 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update Test Metric |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Removed asm 1 & 3 (intent is related to LOE & not milestones); added new asm 2 for clarification & to eliminate possible false trips. | 3, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |