EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A211a

Test Type:

Manual

Attribute/Intent Definition:

06A2:  The network schedule/IMS depicts the sequence of work (horizontal integration) and identifies the significant interdependencies that are indicative of the actual way the work is planned and accomplished.

Test Definition:

Is high total float rationale/justification acceptable?

Test Metric:

X = Count of high total float non-LOE tasks/activities & milestones sampled with inadequate rationale

Y = Total count of high total float non-LOE tasks/activities & milestones sampled

Metric Threshold:

X/Y ≤ 20%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11U EVT

11X Total Float/Slack

11AD Predecessors

11AJ Successors

11AM Task/Activity/Milestone UIDs

11AR CA UIDs

45 IMS Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete tasks/activities & milestones.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Incomplete tasks/activities & milestones equals no actual finish date in the IMS.

Instructions:

- To identify tasks with high float, filter the IMS for incomplete non-LOE tasks/activities & milestones that have total float greater than 44 days.

- Determine sample size from the filtered list in Step 1; this is the denominator (Y) of the test metric.

- Send the list of sample tasks/activities & milestones, including the unique identifier of each task, to the contractor and ask them to provide documented rationale and justification for the total float values of each task/activity & milestone. In lieu of documented rationale, a live demonstration with the responsible CAM(s) and scheduler to provide the rationale and justification can be performed.  Ensure that the rationale and justification addresses:

  - Why were the assigned predecessor(s) and successor(s) chosen for each of the sample tasks/activities & milestones?

  - Why additional or alternate predecessors and/or successors are not needed to reduce the float value?

  - If the rationale provided for a task/activity & milestone does not adequately address the above questions, then that task is considered to have missing/incorrect dependencies (predecessors/successors).

- Count the number of tasks/activities & milestones determined to have missing/incorrect dependencies in Step 3; this is the numerator (X) in the test metric calculation.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 8/16/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | Added “Non-LOE” language, added 2 Data Elements fixed formatting errors |  | 5/24/2019 |
| v3.4 | Update: Attribute, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Updated asm 3 to clarify IMS incomplete CA. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Added “high” when referencing total float for additional clarity | 5, 6, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |