EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A212a

Test Type:

Automated

Attribute/Intent Definition:

06A2:  The network schedule/IMS depicts the sequence of work (horizontal integration) and identifies the significant interdependencies that are indicative of the actual way the work is planned and accomplished.

Test Definition:

Are there out of sequence tasks/activities & milestones?

Test Metric:

X = Count of out of sequence conditions

Metric Threshold:

X = 0

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11C Actual Start Date

11V Forecast Finish Date

11W Forecast Start Date

11AE Predecessor (Type)

11AK Successor (Type)

11AM Task/Activity/Milestone UIDs

45 IMS Data Dictionary

Assumptions:

- Many leads will cause an out of sequence condition.

- S.AS: Successor Actual Start

- S.AF: Successor Actual Finish

- S.FS: Successor Forecast Start

- S.FF: Successor Forecast Finish

- P.AS: Predecessor Actual Start

- P.FS: Predecessor Forecast Start

- P.FF: Predecessor Forecast Finish

- Incomplete tasks/activities & milestones equals no actual finish date in the IMS.

Instructions:

- Identify all the finish-to-start relationships in the IMS containing an incomplete predecessor task/activity or milestone:

  - count the number of successor tasks/activities & milestones that have an actual start date OR a forecast start date before the predecessor forecast finish date [(S.AS or S.FS) < P.FF]

- Identify all the start-to-start relationships in the IMS containing an incomplete predecessor task/activity or milestone:

  - count the number of successor tasks/activities & milestones that have an actual start date OR a forecast start date before the predecessor forecasted start date [(S.AS or S.FS) < P.FS]

- For all the finish-to-finish relationships in the IMS containing an incomplete predecessor task/activity or milestone:

  - count the number of successor tasks/activities & milestones that have an actual finish date OR a forecast finish date before the predecessor forecast finish date [(S.AF or S.FF) < P.FF)]

- For all the start-to-finish relationships in the IMS containing an incomplete predecessor task/activity or milestone:

  - count the number of successor tasks/activities & milestones that have an actual finish date OR a forecast finish date before the predecessor forecast start date [(S.AF or S.FF) < P.FS]

- Add the subtotals from Steps 2 through 5; this is the X of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

- For leads causing out of sequence conditions, determine if there is adequate justification/rationale for the use of leads.

- For out of sequence conditions not caused by leads, determine if there is adequate justification/rationale for the out of sequence condition.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 8/16/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Major change accepted by CCB |  | 2/28/2017 |
| v3.0 | Major changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Improved instruction syntax, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Test Metric, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | Update: Test Metric and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Add “activities” in blk 10 for DECM consistency. Add asm 9 blk 9 to define IMS incomplete. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |