EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A301b

Test Type:

Manual

Attribute/Intent Definition:

06A3: There is vertical schedule integration, i.e., there is consistency of data between various levels of schedules, including subcontractor schedules, and all levels of schedules support the contract/program schedule requirements (e.g., Statement of Work, Design Build Specification, Integrated Master Plan (IMP) etc.).

Test Definition:

Does the IMS baseline finish date align with contractual/CLIN finish (POP) date?

Test Metric:

X = Count of IMS baseline finish dates not in alignment with contractual dates

Metric Threshold:

X = 0

Data Elements Required:

06 Contractual Documents

06B Contractual Milestones

06C Contractual and/or CLIN Period of Performance (PoP)

11 Integrated Master Schedule

11G Baseline Finish Date

45 IMS Data Dictionary

57 Customer Approval for OTS

57A OTS Approval

Assumptions:

- Contractual finish dates include: contract POP; CLIN POP; and milestones delineated within contract.

Instructions:

- Determine the contractual finish date by finding the finish dates within the contract/CLIN or latest contract modifications. Confirm that there is no OTS modifying the POP.

- In the IMS, determine the latest baseline finish date.

- Compare the dates found in Step 2 with the dates found in Step 1. Count IMS baseline finish dates outside the contractual POP; this is the value (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Scheduling CCB |  | 12/2/2015 |
| v2.0 | CCB - validated |  | 9/1/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 08/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 03/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |