EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A401a

Test Type:

Manual

Attribute/Intent Definition:

06A4:  Program milestones, contractual events, program decision points and external dependencies are logically linked within the network schedule/IMS to support critical path analysis.

Test Definition:

Does the schedule tool produce a critical path that represents the longest total duration with the least amount of total float?

Test Metric:

X = Count of tasks/activities & milestones on the constraint method critical path that are not on the contractor’s critical path

Metric Threshold:

X = 0

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11G Baseline Finish Date

11P Constraint Method Critical Path Activities

11Q Constraint Type

11R Contractual milestones

11X Total Float/Slack

11AM Task/Milestone UIDs

12 Program Critical Path

12A Program Critical Path Activities

45 IMS Data Dictionary

Assumptions:

- The constraint method applies a hard constraint to a selected end point with a date earlier than the baseline date of that end point, which generates negative total float and enables the identification of the critical path.

Instructions:

- Request a copy of the contractor’s critical path.

- Using the constraint method, find the critical path through the program completion milestone (i.e. “Contract End”). If no program completion milestone exists, select the final discrete task/activity in the schedule as an alternative and consult with the contractor’s scheduler to determine appropriateness.

- Compare the tasks/activities & milestones on the constraint method critical path to the tasks/activities & milestones on the contractor’s critical path.  Count the total number of tasks/activities & milestones where the critical path calculations do not align (i.e., tasks/activities & milestones that are on the constraint method critical path but not on the contractor’s critical path, or vice versa); this is the value (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 8/16/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Revised Process, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v3.6.1 | Added “milestones” to block 12. Updated block 10 due to oversight. Admin update to include “task” in block 11 |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11 & updated DEs in blk 8. | 8 & 10 | 03/05/2021 |
| v5.0 | Deleted assumption 1 and updated instruction steps 2 and 3 to clarify instruction. Updated blk 10 to include activities and milestones. | 9 & 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |