EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A401b

Test Type:

Manual

Attribute/Intent Definition:

06A4:  Program milestones, contractual events, program decision points and external dependencies are logically linked within the network schedule/IMS to support critical path analysis.

Test Definition:

Are key contractual milestones and events identified in the IMS?

Test Metric:

X = Count of sampled key contractual milestones and events that are not in the IMS

Y = Total count of sampled key contractual milestones and events

Metric Threshold:

X/Y = 0%

Data Elements Required:

04 Contract Statement of Work

04A Contractual Milestones

06 Contractual Documents

06B Contractual Milestones

11 Integrated Master Schedule

11R Contractual Milestones

45 IMS Data Dictionary

Assumptions:

- Test metric is based on a Zero-Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable the test to entire population instead of sampling.

- Typically, key milestones and events are found in Contract Section F (e.g., CLIN Closure Milestones, major deliverables, DD-250, SRR, SFR, PDR, CDR, FFRR, PCA, SSR, SVR, IOT&E, LFT&E, TRR, PRR, IOC, FOC, etc.).

- “Key” milestones and events are defined between the customer and contractor, not by compliance oversight organizations.  If key milestones and events are not defined, the metric defaults to all contractual milestones and events.

Instructions:

- Using contractual documentation, identify a sample of key contractual milestones and events; this is the denominator (Y) of the test metric.

- Identify and count the number of sampled key contractual milestones and events that are not included in the IMS; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| RED | New metric submitted to CCB |  | 2/28/2017 |
| v3.0 | CCB – validated |  | 3/23/2017 |
| v3.1 | Deleted “Incomplete”, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | Update Test Metric |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 03/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |