EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A505b

Test Type:

Automated

Attribute/Intent Definition:

06A5:  The schedule provides baseline, forecast, and actual dates.

Test Definition:

Do all complete tasks/activities & milestones have actual finish dates?

Test Metric:

X = Count of complete tasks/activities & milestones with no actual finish date

Y = Total count of complete tasks/activities & milestones

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11T EV % Complete

11AM Task/Milestone UIDs

13 EV Cost Tool Data

13AN EV% complete

45 IMS Data Dictionary

Assumptions:

- A task/activity or milestone is considered “complete” if EV percent complete = 100%.

- EV percent complete is available at the task/activity & milestone level in the IMS.

- If the EV percent complete field is not available in the IMS, use the EV Cost Tool data to obtain the EV percent complete information for each in progress task/activity & milestone. If the work package level is at the summary level in the IMS, compare the EV percent complete at the IMS summary level to the EV Cost Tool data.

- The scheduling software tool has both an actual start and an actual finish date for a milestone; if this is not the case, adjust the methodology accordingly.

- Summary tasks/activities are not included.

Instructions:

- Identify and count the total number of complete tasks/activities & milestones where EV percent complete is 100%; this is the denominator (Y) of the metric.

- Identify and count the number of complete tasks/activities & milestones from Step 1 that have no actual finish date; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Minor change submitted to CCB |  | 2/28/2017 |
| v3.0 | Minor changes accepted by CCB |  | 3/28/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Update: Test Step, Test Metric, Data Elements Required, Assumptions, and Instructions |  | 8/30/2020 |
| v3.6.1 | Added “& milestones” and “task” in block 11. Updated capitalization of Cost Tool |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Added “in the IMS” blk 9 asm 2 & updated asm 3 to align with 06A505a asm 3. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Added assumption 5 to align to other GL6 metric changes approved in v4.0 | 9 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |