EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A506a

Test Type:

Automated

Attribute/Intent Definition:

06A5:  The schedule provides baseline, forecast, and actual dates.

Test Definition:

Are actual start and actual finish dates valid for all tasks/activities & milestones in the IMS?

Test Metric:

X = Count of tasks/activities & milestones with either actual start or actual finish after status date

Y = Total count of tasks/activities & milestones with an actual start date

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11C Actual Start Date

11AG Status Date

11AM Task/Activities/Milestone UIDs

45 IMS Data Dictionary

Assumptions:

- A task/activity or milestone where both actual start and actual finish dates are after the status date is only counted as a single deficiency.

Instructions:

- Identify and count all tasks/activities & milestones in the IMS with an actual start date; this is the denominator (Y) of the metric.

- Identify the status date of the IMS.

- Identify and count all tasks/activities & milestones with actual start dates after the status date, actual finish dates after the status date, or both; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Added actual start date specification in instructions |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Add “task” & “milestone” in blk 9 for DECM consistency and steps clarity. Replace "discrepancy" for "deficiency" to be consistent with the overarching 2303-01 | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |