EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06I101b

Test Type:

Manual

Attribute/Intent Definition:

06I1:  Schedule margin, an optional management method for accommodating schedule contingencies, must be traceable to the risk register and consistently identifiable in the IMS.

Test Definition:

Do schedule margin tasks/activities represent risk impact to subsequent significant events/milestones?

Test Metric:

X = Count of schedule margin tasks/activities that do not represent risk impact to subsequent events/milestone

Metric Threshold:

X = 0

Data Elements Required:

03 EVM System Description

11 Integrated Master Schedule

11C Actual Start Date

11A Actual Finish Date

11AJ Successors

11AM Task/Activity/Milestone UIDs

45 IMS Data Dictionary

62 Risk Management Process/ Plan

Assumptions:

- Schedule margin tasks/activities exist in the IMS; if no schedule margin tasks/activities exist, this metric is not applicable.

Instructions:

- Identify and count all schedule margin tasks/activities:

  - with duration not defensible through a formal Risk Management process

  - with Actual Start date not equal to Actual Finish date

  - with a successor other than a key contractual event, significant logical integration/test event, end item deliverable, or contract completion

  - not identified in the IMS as defined in the contractor’s EVMS

- Add the number of schedule margin tasks/activities identified in step 1; this is the value (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v3.1 | Initial |  | 11/28/2018 |
| v3.3 | Added Data Element 11E |  | 5/24/2019 |
| v3.4 | Update: Test Step, Test Metric, and Instructions |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Update Instructions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Add “/activities” for DECM consistency. Updated attribute number in blk 4 to match DECM tracker and methodology. | 4, 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Corrected Data Elements 11CA and 11AC; added Data Elements 03 and 62; | 8 | 12/7/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |