EVMS Test Metric Specification

Guideline No:

- 07

Test Metric ID:

07A102b

Test Type:

Manual

Attribute/Intent Definition:

07A1:  Objective completion criteria aligned with the accomplishment of the program’s technical requirements and goals are determined in advance, documented, and used to plan and measure the progress of program milestones and events.

Test Definition:

Is the IMP traceable to the IMS?

Test Metric:

X = Count of IMP criteria that are not represented in the IMS

Y = Total count of IMP criteria

Metric Threshold:

X/Y = 0%

Data Elements Required:

03 EVM System Description

10 Integrated Master Plan

10A IMP Code

11 Integrated Master Schedule

11Y IMP Code

45 IMS Data Dictionary

Assumptions:

- The IMP criteria are traceable to the IMS at the lowest level specified by the EVM SD.

- If an IMP is not required on the program, then this metric is not applicable.

Instructions:

- Identify and count the total number of IMP criteria; this is the denominator (Y) of the metric.

- Identify and count the number of IMP criteria that are not represented in the IMS; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Major change accepted by CCB |  | 2/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Changed to Manual, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11 up updated DE blk 8 to align with test asm 1. | 8 & 10 | 3/05/2021 |
| v5.0 | Updated assumption 2 to include situations where IMP is not required by contract. | 9 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |