EVMS Test Metric Specification

Guideline No:

- 08

Test Metric ID:

08I103a

Test Type:

Automated

Attribute/Intent Definition:

08I1: For future effort that cannot practically be identified to a control account, it is permissible to establish a SLPP above the control account level that identifies scope, schedule, and associated budget to the end of the contract.

Test Definition:

Have SLPPs earned performance?

Test Metric:

X = Count of SLPPs with BCWPCUM

Y = Total count of SLPPs

Metric Threshold:

X/Y ≤ 2%

Data Elements Required:

13 EV Cost Tool Data

13Q BCWPCUM

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- None

Instructions:

- Identify and count the total number of SLPPs; this is the denominator (Y) of the test metric.

- Identify and count SLPPs that have earned performance (BCWPCUM is not zero); this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v3.3 | Initial |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Updated attribute number in blk 4 to match DECM tracker and methodology. | 4, 8, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated assumptions to say “None” | 9 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |