EVMS Test Metric Specification

Guideline No:

- 09

Test Metric ID:

09A102a

Test Type:

Manual

Attribute/Intent Definition:

09A1:  Work authorization process/documentation identifies work scope description, budgets segregated by elements of cost (i.e., direct labor dollars/hours, material dollars, subcontract dollars, and other direct costs), and period of performance for the authorized effort.

Test Definition:

Is work authorization date prior to the incurrence of actual costs?

Test Metric:

X = Count of sampled incomplete CAs where ACWP incurred before the work authorization date

Y = Total count of sampled incomplete CAs that have incurred actual costs

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting/Fiscal Calendar

02A Accounting Month Dates

09 Work Authorization Documentation (WAD)

09A Approval Date

13 EV Cost Tool Data

13C ACWPCUM

13G ACWPCUR (of selected months)

13K BAC for CA and SLPP

44 Cost Data Dictionary

Assumptions:

- Initial determination of attribute risk is based on a sample of incomplete CAs, with threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- Applies to initial and current/revised work authorization documentation.

- Baseline start and finish dates are to be assessed according to Accounting/Fiscal Calendar month.

- Exact dates inclusive of the day (e.g. MM/DD/YYYY) carried in the EV Cost Tool data are not utilized for this metric.

Instructions:

- Identify a sample of incomplete CAs in the EV Cost Tool data that have incurred actual costs; this is the denominator (Y) of the test metric.

- Count the number of sampled incomplete CAs where actuals were incurred in an accounting/fiscal month prior to work authorization approval; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Major change submitted to CCB |  | 2/28/2017 |
| v3.0 | Major changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Admin update to capitalize “Cost Tool”. Added “data” for DECM consistency. Updated blk 8 for DECM consistency & added data element 44 to supplement artifact 13. Added “or” blk 9 to correct oversight. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |