EVMS Test Metric Specification

Guideline No:

- 09

Test Metric ID:

09A103a

Test Type:

Automated

Attribute/Intent Definition:

09A1:  Work authorization process/documentation identifies work scope description, budgets segregated by elements of cost (i.e., direct labor dollars/hours, material dollars, subcontract dollars, and other direct costs), and period of performance for the authorized effort.

Test Definition:

Are elements of cost defined/identified for each control account?

Test Metric:

X = Sum of BAC for incomplete CAs with budgets that cannot be segregated by element of cost

Y = Total BAC of incomplete CAs

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13H BAC

13Q BCWPCUM

13AJ Element of Cost

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- If the element of cost segregation is at a level lower than the CA, any EOC missing at the lower level trips the CA.

Instructions:

- Sum the total BAC for incomplete CAs; this is the denominator (Y) of the test metric.

- Identify any incomplete CAs with budgets not segregated by element of cost, and sum the BAC of those CAs; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Major change submitted to CCB |  | 2/28/2017 |
| v3.0 | Major changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Admin update to capitalize “Cost Tool”. Added “data” for DECM consistency. Updated blk 8 for DECM consistency & added data element 44 to supplement artifact 13. Added “or” blk 9 to correct oversight. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |