EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A109b

Test Type:

Automated

Attribute/Intent Definition:

10A1:  Work packages have the following characteristics:

- Represent the scope of work at the level where work is performed or aggregated.

- Are distinguishable from all other work packages.

- Are assigned to a single organizational element.

- Include scheduled start and completion dates; and as applicable, interim milestones, all of which are representative of technical accomplishment.

- Have a time-phased budget or value expressed in terms of dollars, labor hours, or other measurable units that is substantiated in terms of supporting project plans.

- Have durations that are limited to a span of time that is practical for the work scope.  Longer-duration work packages have interim objective measures, such as points of technical achievement, to enable accurate performance assessment.

- Are identified within the Integrated Master Schedule (IMS) and other supporting schedules.

Test Definition:

Does each WP/PP/SLPPs have an assigned budget?

Test Metric:

X = Count of WPs/PPs/SLPPs with BAC ≤ 0

Y = Total count of WPs/PPs/SLPPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13H BAC

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- If scope has been assigned to the WPs/PPs/SLPPs that tripped this metric, but BAC ≤ 0, GL8 also needs to be investigated to determine if the PMB is accurate. An accurate baseline would be scope that also has corresponding schedule and budget.

- Use rounding to the nearest dollar as a whole number verifying BAC.

- Test Metric is performed with WPs, all PPs (GL10 – Attribute 3), and all SLPPs (GL 8 – Attribute 1).

- If trips are accruing ACWP, then they might warrant further investigation. Rounding is not applicable to ACWP.

Instructions:

- Identify and count all WPs/PPs/SLPPs; this is the denominator (Y) of the test metric.

- Identify and count all WPs/PPs/SLPPs where BAC is negative or zero; this is the numerator (X).

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB – validated & merged with 21A501a |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Minor Changes, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Update ensures that the analysis is focused on co-mingling of EOC to cover intent of deleted 10A202a. Also, to cover removed scope from 10A105a that verifies QBD on how performance is claimed for material. | 4, 5, 8, 9, 10 | 3/05/2021 |
| v5.0 | Added assumption 2 to reference other applicable GL attributes. Fixed assumption 1 to reference WPs vice CAs. Updated WP complete assumption to align with other metrics. | 9 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |