EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A302a

Test Type:

Automated

Attribute/Intent Definition:

10A3:  Planning packages have the following characteristics:

- Are the logical aggregations of work within a control account, normally the far-term effort that can be identified, budgeted, and time-phased in baseline planning, but cannot yet be detail planned into work packages.

- Are identified within the Integrated Master Schedule (IMS) and other supporting schedules.

Test Definition:

Have PPs incurred actual costs?

Test Metric:

X = Count of PPs with ACWPCUM

Y = Total count of PPs

Metric Threshold:

X/Y ≤ 2%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13H BAC

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP/PP).

- When ACWP is collected at the CA level, if a CA has accrued ACWP (ACWPCUM is not zero), and the CA only contains PPs (i.e., no WP with BAC > 0 within CA), all PPs belonging to the CA must be counted in the numerator.

Instructions:

- Identify and count the total number of PPs; this is the denominator (Y) of the test metric.

- Identify and count PPs that have incurred actual costs (ACWPCUM is not zero); this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Block 10: Replaced Artifact |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Updated Data Elements & asms. Change will make it possible to assess intent where ACWP is collected, including at CA level. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |