EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A303a

Test Type:

Automated

Attribute/Intent Definition:

10A3:  Planning packages have the following characteristics:

- Are the logical aggregations of work within a control account, normally the far-term effort that can be identified, budgeted, and time-phased in baseline planning, but cannot yet be detail planned into work packages.

- Are identified within the Integrated Master Schedule (IMS) and other supporting schedules.

Test Definition:

Do all PPs have duration?

Test Metric:

X = Count of PPs (tasks/activities & milestones level) with baseline duration less than or equal to one day

Y = Total count of PPs (tasks/activities & milestones level)

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

11 Integrated Master Schedule

11F Baseline Duration

11U EVT

11AM Task/Activity/Milestone UIDs

11AP WP/PP/SLPP UIDs

11AS Planning Level Code

45 IMS Data Dictionary

Assumptions:

- IMS contains EVT and/or Planning Level Code Field.

Instructions:

- Identify and count the total number of tasks/activities & milestones identified as PPs based on EVT or Planning Level Code; this is the denominator (Y) of the test metric.

- Identify and count the total number of tasks/activities & milestones identified in step 1 that have baseline duration less than or equal to one day; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Block 10: Replaced Artifact, adjusted BL Duration to <1 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update: Test Metrics and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 &10 | 3/05/2021 |
| v5.0 | Updated blk 6 & 10 to define level at which PP is identified. Updated data elements to align to other metrics and create new data element if PP not identified by EVT field. | 6, 8, 9, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| V7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |