EVMS Test Metric Specification

Guideline No:

- 11

Test Metric ID:

11A101a

Test Type:

Automated

Attribute/Intent Definition:

11A1:  The sum of all work package budgets plus planning package budgets within control accounts equals the budgets authorized for those control accounts.

Test Definition:

For all CAs, does the BAC for the CA equal the sum of the WP and PP budgets within the CA?

Test Metric:

X = Sum of the absolute values of (CA BAC – the sum of its WP and PP budgets)

Y = Total program BAC

Metric Threshold:

X/Y ≤ 1%

Data Elements Required:

13 EV Cost Tool Data

13J BAC (for CAs)

13M BAC (for WPs and PPs)

13AA CA UIDs

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Metric tests the sum of CA budgets, not individual CAs.

- When the contractor uses an off-the-shelf EVM tool set to execute a roll-up function from lowest level to highest level, DCMA or SUPSHIP will confirm that the tool set performs the calculation as an initial test only until such time as a tool set change or major upgrade occurs.

- If not using an off-the-shelf EVM tool set to calculate variances, the test metric must be performed manually.

- Use rounding to the nearest whole number for the sum of CA and WP budgets (BAC).

Instructions:

- Sum the budgets (BAC) for all CAs; this is the denominator (Y) of the test metric.

- For each CA, sum the budgets of all WPs and PPs within it.

- Take the sum calculated in Step 2 and subtract it from the CA BAC.

- Sum the absolute values of any differences calculated in Step 3; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v1.1 | Edited and returned for retest |  | 6/22/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data elements 44 & 45 to supplement artifacts 11 & 13, and updated blk 8 Data Elements for DECM consistency. Updated blk 9 asm 3 to align with definition of LOE complete discussed and approved on CCB 1/20/21 to add “and ETC is less than $100”. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |