EVMS Test Metric Specification

Guideline No:

- 12

Test Metric ID:

12A101a

Test Type:

Manual

Attribute/Intent Definition:

12A1:  Work packages planned as LOE contain efforts of a general or supportive nature that do not produce technical content leading to an end item or product.

Test Definition:

Are the contractor’s Level of Effort (LOE) WPs supportive in nature and/or do not produce technical content leading to an end item or product?

Test Metric:

X = Sum of BAC of sampled incomplete LOE WPs that are not supportive in nature and/or produce technical content leading to an end item or product

Y = Total BAC of sampled incomplete LOE WPs

Metric Threshold:

X/Y ≤ 15%

Data Elements Required:

03 EVM System Description

03V Process for LOE/discrete work decomposition

04 Contract Statement of Work (CSOW)

04B SOW paragraphs

05 WBS Dictionary

05A SOW references

09 Work Authorization Documents (WAD)

09G Scope description

11 Integrated Master Schedule (IMS)

11A Actual Finish Date

11U EVT

11AP WP/PP/SLPP UIDs

13 EV Cost Tool Data

13M BAC for WP

13Q BCWPCUM

13AL ETC

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete LOE WPs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

Instructions:

- Review the contractor’s System Description to determine if a process is in place to ensure LOE WPs are supportive in nature and/or do not produce technical content leading to an end item or product.

- If a process is in place to ensure LOE WPs are supportive in nature, go to Step 3; if a process is not in place, go to Step 6.

- If LOE is less than 15% of the remaining work for the contract, test is complete. Otherwise, proceed to Step 4.

- Select a sample of incomplete LOE WPs from the EV Cost Tool data or Integrated Master Schedule to determine if the contractor is following the prescribed process; the sum of BAC for the sampled LOE WPs is the denominator (Y) of the test metric.

- Sum the BAC of the sampled LOE WPs from Step 4 that do not follow the prescribed process; this is the numerator (X) of the test metric.  Skip to Step 8.

- Select a sample of incomplete LOE WPs from the EV Cost Tool data or Integrated Master Schedule to determine if the LOE WPs are supportive in nature; the sum of BAC for the sampled LOE WPs is the denominator (Y) of the test metric.

- For the sampled LOE WPs from Step 6, review WP descriptions and/or WADs to identify those sampled LOE WPs that are not supportive in nature; the sum of the BAC of these WPs is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v1.1 | Edited and returned for retest |  | 6/22/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data elements 44 & 45 to supplement artifacts 11 & 13, and updated blk 8 Data Elements for DECM consistency. Updated blk 9 asm 3 to align with definition of LOE complete discussed and approved on CCB 1/20/21 to add “and ETC is less than $100”. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |