EVMS Test Metric Specification

Guideline No:

- 12

Test Metric ID:

12A201a

Test Type:

Manual

Attribute/Intent Definition:

12A2: Work packages planned as LOE are separately evaluated from discrete within the control account.

Test Definition:

Are LOE WPs separately evaluated from non-LOE WPs within the same control account?

Test Metric:

X = Count of sampled incomplete CAs requiring VARs that have LOE and non-LOE WPs where cost performance of LOE work and cost/schedule performance of non-LOE work is not separately evaluated

Y = Total count of sampled incomplete CAs requiring VARs that have LOE and non-LOE WPs

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13J BAC for CA

13Q BCWPCUM

13AD Cumulative Cost Variance

13AE Cumulative Schedule Variance

13AF Current Cost Variance

13AG Current Schedule Variance

13AP EVT

13AY Variance at Complete

15 Internal Variance Analysis Thresholds

15A Internal variance analysis thresholds

16 VARs

16A VARs

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the CA is complete.

- If costs cannot be separately identified for LOE and non-LOE work for commingled (LOE & non-LOE) control accounts (e.g., through cost collection below the CA level or through charge numbers segmenting costs for LOE and non-LOE work), then the metric does not apply.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Select a sample of incomplete commingled control accounts that require Variance Analysis Reports (VARs); this is the denominator (Y) of the test metric.

- For each CA identified in Step 1, count the number of CAs that have VARs that do not separately evaluate performance of LOE and non-LOE work; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v1.1 | Edited and returned for retest |  | 6/22/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated DE in blk 8 for DECM consistency. Added data element 44 to supplement artifact 13. Admin updated numbering oversight in blk 10 step 2. Updated blk 9 asm 3 to align with definition of LOE complete discussed and approved on CCB 1/20/21 to add “and ETC is less than $100”. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Updated language to “non-LOE” to account for WPs that are neither LOE or Discrete. | 5,6,9,10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |