EVMS Test Metric Specification

Guideline No:

- 14

Test Metric ID:

14A101a

Test Type:

Automated

Attribute/Intent Definition:

14A1:  MR has no scope defined and is separately identified outside of the PMB.

Test Definition:

Is MR excluded from the PMB?

Test Metric:

X = Absolute value of (MR - (TAB - PMB))

Y = MR

Metric Threshold:

X/Y = 0%

Data Elements Required:

20 IPMR/CPR/IPMDAR

20K Format 1 PMB / CPD Summary Performance PMB

20N Format 1 TAB / CPD Contract Data

41 Budget (MR) Log

41F MR

Assumptions:

- Total rounding error of $1,000 or less due to IPMR/CPR/IPMDAR reporting precision is not considered a deficiency.

Instructions:

- Identify/calculate TAB and PMB values using the IPMR/CPR/IPMDAR, and identify the MR value from the budget log.

- MR is the denominator (Y) of the test metric.

- Subtract the PMB from the TAB.

- Subtract the amount derived in Step 3 from MR and take the absolute value of the result; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Replaced "discrepancy" with "deficiency" in blk 9 to be consistent with the overarching 2303-01. | 9 &10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8, 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |