EVMS Test Metric Specification

Guideline No:

- 14

Test Metric ID:

14A201a

Test Type:

Automated

Attribute/Intent Definition:

14A2:  UB has defined scope, is separately identified, traceable to contractual actions and is part of the PMB.

Test Definition:

Is UB included in the PMB?

Test Metric:

X = Absolute value of (UB - (PMB - Distributed Budget))

Y = UB

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13K BAC for CAs and SLPPs

20 IPMR/CPR/IPMDAR

20K PMB/ CPD Summary Performance PMB

41 Budget Log

41J UB

44 Cost Data Dictionary

Assumptions:

- Total rounding error of $1,000 or less due to IPMR/CPR/IPMDAR reporting precision is not considered a deficiency.

Instructions:

- Identify the PMB value using the IPMR/CPR/IPMDAR and the UB value from the budget/UB log.

- UB value is the denominator (Y) of the test metric.

- Identify Distributed Budget using EV Cost Tool data to calculate the sum of CA and SLPP budgets (BAC).

- Subtract the Distributed Budget calculated in Step 3 from the PMB.

- Subtract the amount derived in Step 4 from UB and take the absolute value of the result; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated capitalization of “data” in blk 10 for DECM consistency. Added data element 44 to supplement artifact 13. Change “discrepancy" for "deficiency" to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8, 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |