EVMS Test Metric Specification

Guideline No:

- 14

Test Metric ID:

14A202a

Test Type:

Manual

Attribute/Intent Definition:

14A2:  UB has defined scope, is separately identified, traceable to contractual actions and is part of the PMB.

Test Definition:

Does UB have defined scope and is traceable to contractual actions?

Test Metric:

X = Count of sampled UB transactions without defined scope/not traceable to contract actions

Y = Total count of sampled UB transactions

Metric Threshold:

X/Y ≤ 20%

Data Elements Required:

18 Baseline Control Logs

18D Baseline Changes Involving UB Transactions

41 Budget Log

41K UB Transactions

43 Baseline Change Request

43G UB Transaction Substantiation

Assumptions:

- Test metric is based on a random sample of UB transactions within the prior 12 month period.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Identify a sample of baseline changes involving UB transactions within the prior 12 month period; this is the denominator (Y) of the test metric.

- Review the selected UB transactions in the baseline change documentation (e.g., BCRs) or UB log to ensure that UB has defined scope and is traceable to contractual actions.

- Count the sampled UB transactions that do not have defined scope and/or are not traceable to contractual actions; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB – validated with changes |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Test Metric, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |