EVMS Test Metric Specification

Guideline No:

- 16

Test Metric ID:

16A101a

Test Type:

Manual

Attribute/Intent Definition:

16A1:  The ACWP in the EVMS reconciles to the direct costs in the accounting system.

Test Definition:

Does ACWPCUM in the EVMS reconcile to actual costs in the accounting system?

Test Metric:

X = Sum of actual direct costs that do not reconcile between the EV Cost Tool and the Accounting System

Y = Sum of total direct ACWPCUM from the EV Cost Tool

Metric Threshold:

X/Y ≤ 1%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

14 Accounting System Data

14C Contract Level Cumulative Actual Direct Costs

44 Cost Data Dictionary

54 Actual Cost Reconciliation

54A Actual Cost Reconciliation

Assumptions:

- Test is performed at the total contract/program level.

- Total contract level cumulative actual costs are generated via an aggregation of control account data.

- Acceptable reconciliation for deficiencies between the Accounting System and EV Cost Tool data actual costs includes estimated actuals, unallowable costs, etc.

- Differences due to rounding error (within +/- $100) are not counted as deficiencies.

Instructions:

- Calculate total contract level cumulative actual direct cost (ACWPCUM) from the EV Cost Tool data; this is the denominator (Y) of the test metric.

- Calculate total contract level cumulative actual direct cost from the Accounting System.

- Reconcile any difference between the values obtained in Steps 1 and 2.  Identify the remaining total actual costs that cannot be reconciled; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB | All | 2/17/2016 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Added Rounding $100 rounding error Assumption |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “Cost Tool” for DECM consistency. Admin update to capitalize “Cost Tool”. Added data element 44 to supplement artifact 13. Replaced "discrepancy" for "deficiency" - to be consistent with the overarching 2303-01. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |