EVMS Test Metric Specification

Guideline No:

- 16

Test Metric ID:

16A501a

Test Type:

Automated

Attribute/Intent Definition:

16A5:  ACWP is recorded in the same accounting period that BCWP is earned.

16A6:  Actual costs for work accomplished are transferred to the EVMS for a valid comparison of ACWP to BCWP for the same work in the same accounting period.

Test Definition:

Is Non-Material ACWP being recorded without BCWP?

Test Metric:

X = Absolute value of Non-Material, Non-LOE ACWPCUR on incomplete CAs/WPs where Non-Material, Non-LOE ACWPCUR ≠ 0 and Non-Material, Non-LOE BCWPCUR = 0

Y = Absolute value of total Non-Material, Non-LOE ACWPCUR on incomplete CAs/WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13F ACWPCUR (Non-Material)

13H BAC

13T BCWPCUR (Non-Material)

13Q BCWPCUM

13AJ Element of Cost

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP).

- Includes only incomplete CAs/WPs filtered on Non-Material, Non-LOE EOCs (Material cost is tested under a separate guideline).

- If Non-Material BAC and BCWPCUM are within $100 (or 1 hour), then the CA/WP is considered complete.

- Adjustments for estimated actuals are not considered a deficiency.

- PPs are excluded from this metric when it is performed at the WP level.

- When ACWP is collected at the CA level, LOE and non-LOE are included on this metric

- Use rounding to the nearest whole number for  BCWPCUR and  ACWPCUR.

Instructions:

- Filter out material EOCs, then use assumption to determine incomplete CAs/WPs.

- Sum of the absolute values of Non-Material, Non-LOE ACWPCUR on incomplete CAs/WPs; this is the denominator (Y) of the test metric.

- Identify incomplete CAs/WPs where Non-Material, Non-LOE ACWPCUR ≠ 0 and BCWPCUR = 0.

- Sum of the absolute values of all ACWPCUR for the Non-Material, Non-LOE incomplete CAs/WPs identified in Step 3; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB | All | 2/17/2016 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Added Rounding $100 rounding error Assumption |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “Cost Tool” for DECM consistency. Admin update to capitalize “Cost Tool”. Added data element 44 to supplement artifact 13. Replaced "discrepancy" for "deficiency" - to be consistent with the overarching 2303-01. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |