EVMS Test Metric Specification

Guideline No:

- 19

Test Metric ID:

19A101b

Test Type:

Manual

Attribute/Intent Definition:

19A1:  The cost accumulation system provides for the accurate allocation of indirect costs based on documented procedures.

Test Definition:

Are the bases and rates for allocating costs from each indirect pool consistently applied?

Test Metric:

X = Count of sampled indirect rates that do not match between published rates and the rate applied in the EVMS cost report

Y = Total count of sampled indirect rates

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13A Monthly Overhead Cost Accumulation (by Overhead Pool)

23 CASB Disclosure Statement

23B Method of Application of Indirect Rates to Direct Costs

24 FPRA/FPRP (or published indirect rates)

24C Published Indirect Rates

44 Cost Data Dictionary

Assumptions:

- This metric does not apply if indirect burdens are applied in the Accounting System.  If direct hours or labor dollars in the Accounting System are transferred to the EV Cost Tool, and indirect rates are applied in the EV Cost Tool, then this test is performed.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Test is conducted at the level where actual costs are collected (CA or WP).

- An EVMS cost report can be generated showing the rates applied to direct (unburdened) costs and the total burdened costs at the level actual costs are collected in the EV Cost Tool.  If not, there is a report that shows the unburdened costs and burdened costs separately for each overhead pool, including each Cost of Money (COM) pool and General and Administrative (G&A) pool to derive the rate applied.

Instructions:

- Using the Disclosure Statement, verify the method for application of indirect rates to direct costs.

- Obtain an EVMS cost report showing monthly overhead cost accumulation, at the level actual costs are collected, for the current time period for each overhead pool.

- Select a sample of at least five CAs/WPs (at the level where costs are collected) and calculate the indirect rate applied by dividing the burdened cost by the unburdened cost.  Verify the rates derived from the EVMS cost report match the current published indirect rates.  Count each instance where the indirect rates for actuals do not match between the published rates and the rates derived from the EVMS cost report; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| 0 | New | All | 1/27/2016 |
| v2.0 | CCB – validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Updated capitalization for DECM consistency. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Added assumption 2 for zero based sampling | 9 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |