EVMS Test Metric Specification

Guideline No:

- 20

Test Metric ID:

20A101a

Test Type:

Manual

Attribute/Intent Definition:

20A1:  The contractor’s system can to provide unit costs, equivalent unit or lot costs in terms of labor, material, other direct costs, and indirect costs as required by the contract.

Test Definition:

If required, is the contractor’s system capable of reporting in unit or lot costs in a production or manufacturing environment?

Test Metric:

X = System that cannot produce reports in unit or lot costs in terms of labor, material, other direct costs, and indirect costs derived from the accounting system

Metric Threshold:

X = 0

Data Elements Required:

06 Contractual Documents

06E Requirement to Report Unit or Lot Costs

14 Accounting System Data

14B Capability to Report Unit or Lot Costs

Assumptions:

- If unit costs, equivalent unit or lot costs in terms of labor, material, other direct costs, and indirect costs are not required by the contract/program, then this metric is not applicable.

Instructions:

- Verify that the contractor’s system is capable of producing reports in unit costs, equivalent unit or lot costs in terms of labor, material, other direct costs, and indirect costs.  Record if the system is not capable of producing unit/lot cost reports (X = 1).

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 9/14/2015 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |