EVMS Test Metric Specification

Guideline No:

- 20

Test Metric ID:

20A201a

Test Type:

Manual

Attribute/Intent Definition:

20A2:  Recurring or nonrecurring costs can be identified as necessary or required by the contract.

Test Definition:

If required, are the cost accumulation structures established identifying recurring/non-recurring costs?

Test Metric:

X = System that cannot produce reports in terms of recurring or nonrecurring costs derived from the accounting system

Metric Threshold:

X = 0

Data Elements Required:

06 Contractual Documentation

06D Requirement to Report Recurring/Non-recurring Costs

14 Accounting System Data

14A Capability to Report Recurring/Non-recurring Costs

Assumptions:

- If recurring/non-recurring cost reporting is not required by the contract/program, then this test is not applicable.

Instructions:

- Verify that the contractor’s system is capable of producing reports in terms of recurring/non-recurring costs.  Record if the system is not capable of producing recurring/non-recurring cost reports (X=1).

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 9/14/2015 |
| v2.0 | CCB – validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| V7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |