EVMS Test Metric Specification

Guideline No:

- 21

Test Metric ID:

21A401a

Test Type:

Manual

Attribute/Intent Definition:

21A4: Control account plans demonstrate time-phased material budgets and earned value technique (EVT); these plans allow traceability of high-value/critical materials.

21A5: Material categories are identified and aligned to the type of progressing methodology to be used, (e.g., point of receipt, inspection, and acceptance; point of issue, technical accomplishment for progress payments, etc.)

with the appropriate EVT.

Test Definition:

Are material EVTs implemented per the contractor’s procedures?

Test Metric:

X = BAC of sampled incomplete material WPs with LOE, PERT, Apportioned, or blank EVT not implemented per the contractor’s procedures.

Y = Total BAC of sampled incomplete LOE, PERT, Apportioned, or blank EVT material WPs

Metric Threshold:

X/Y ≤ 0%

Data Elements Required:

03 EVM System Description

03A Material Categorization Process

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AK Element of Cost (Material)

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete material WPs.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If the contractor’s procedures do not define a Material Categorization Process , all material shall be considered discrete or this test is out of threshold.

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- The Cost Data Dictionary defines all EVTs used. When EVT from the EV Cost Tool is of a %Complete type and additional information is not provided in the Cost Data Dictionary, performance substantiation is tested under DECM 10A201a.

- The Program Evaluation and Review Technique (PERT) Cost Formula is used to calculate BCWP by comparing the actual cost of received material (ACWP) to the expected total cost for that material (EAC) and applying the resulting percentage to the originally budgeted value for the material (Budget at Complete (BAC)), BCWP = (ACWP/EAC) x BAC. Any quantifiable backup data or other supporting documentation that relies on a formula based on actuals and estimates (cost or quantity) is treated as PERT in this test regardless of naming convention (e.g., usage driven, statistical method, expenditure method, earned as spent).

Instructions:

- Review the contractor’s procedures to determine how material is categorized and the acceptable earned value techniques for the different categories.

- Identify a sample of incomplete material WPs with LOE, PERT, Apportioned, or blank EVT, and sum their BAC; this is the denominator (Y) of the test metric.

- Using the sample identify in Step 2, sum of the BAC for all WPs with LOE, PERT, Apportioned, or blank EVT not implemented per the contractor’s procedures; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Accounting CCB | All | 02/17/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Added “incomplete” to the test metric section |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update: Test Step, Test Metric, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated data elements on blk 8 for DECM consistency. | 8 & 10 | 3/05/2021 |
| v5.0 | Redefined metric to target specific types of EVTs to determine if appropriate and not focus on high-value/critical materials. Updated threshold to zero and included standard zero based sampling assumption. Updated data element to include redefined 03A. | 4, 5, 6, 7, 8, 9, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |