EVMS Test Metric Specification

Guideline No:

- 21

Test Metric ID:

21I101a

Test Type:

Manual

Attribute/Intent Definition:

21I1:  The material accounting system provides full accountability for all material (including residual inventory) purchased for a program.  Documentation of the systemic approach to how material transfers, rework, and scrap are handled is required to ensure appropriate collection of direct costs and performance measurement.

Test Definition:

Are material transfers and loans processed to ensure appropriate collection of direct costs and performance measurement?

Test Metric:

X = Count of sampled material transfers and loans not processed correctly

Y = Total number of sampled material transfers and loans

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

13 EV Cost Tool Data

13E ACWPCUR

13S BCWPCUR

14 Accounting System Data

14G Material Transfers/Loans

29 MRP/ERP System Data

29B Material Transfers/Loans

44 Cost Data Dictionary

Assumptions:

- Test is based on a sample of material transfers/loans.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Identify a sample of material transfers/loans; this sample size is the denominator (Y) of the test metric.

- Review the supporting documentation for each of the material transfers/loans in the sample, and verify that the contractor is following its documented process.  Ensure BCWP and ACWP are updated/transferred as applicable.  Count the number of material transfers/loans that were incorrectly processed; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Accounting CCB |  | 2/17/2016 |
| v2.0 | CCB – resubmitted for testing; validated |  | 6/21/2016 |
| v2.1 | Integration – Given UID (was 21IXXXa) |  | 9/8/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Updated attribute number in blk 4 to match DECM tracker and methodology. | 4, 8, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |