EVMS Test Metric Specification

Guideline No:

- 22

Test Metric ID:

22I102a

Test Type:

Automated

Attribute/Intent Definition:

22I1:  To ensure cost and schedule variances are valid, the EVM method used to derive the BCWP must be consistent with the method used to plan and resource the associated work.

Test Definition:

Is performance greater than budget (BAC)?

Test Metric:

X = BCWPCUM for WPs where BCWPCUM is greater than BAC

Y = Total BCWPCUM for all WPs

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- If BCWPCUM is greater than BAC by less than $100 (or less than 1 hour), then it is not considered a deficiency.

- PPs and SLPPs are not included.

Instructions:

- Sum BCWPCUM for all WPs in the EV Cost Tool data; this is the denominator (Y) of the test metric.

- Identify WPs where BCWPCUM is greater than BAC.

- Sum BCWPCUM for all WPs identified in Step 2; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | New UID to align with GL 22 Intent (CCB) |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Added Assumption 2 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated data elements on blk 8 for DECM consistency. Replaced "discrepancy" with "deficiency" in blk 9 as 1 to be consistent with the overarching 2303-01. Updated attribute number in blk 4 to match DECM tracker and methodology. | 4, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |