EVMS Test Metric Specification

Guideline No:

- 23

Test Metric ID:

23A201a

Test Type:

Manual

Attribute/Intent Definition:

23A1:  Schedule and cost variances are identified and analyzed at control account and summary level.

23A2:  The variance analysis identifies the factors causing the variance (e.g., efficiency, rate, and timing) and potential impacts.

- Labor cost variance analysis is substantiated from source records evaluating rate and volume variances.

- Material cost variance analysis is substantiated from source records evaluating price and usage variances.

Test Definition:

Are Rate & Volume (Labor) and Price & Usage (Material) Variance formulas correctly applied at the control account level?

Test Metric:

Verify formulas:

Labor

Rate Variance = (Earned Rate - Actual Rate) * Actual Hours

Volume Variance = (Earned Hours - Actual Hours) * Earned Rate

Material

Price Variance = (Earned Unit Price - Actual Unit Price) * Actual Quantity

Usage Variance = (Earned Quantity - Actual Quantity) * Earned Unit Price

Metric Threshold:

Within Threshold / Out of Threshold

Data Elements Required:

17 Variance Analysis Reports (VARs)

17B Price Variance (PV) Formula

17C Usage Variance (UV) Formula

17D VARs

17E Rate Variance (RV) Formula

17F Volume Variance (VV) Formula

Assumptions:

- Budgeted Labor Rate is equivalent to Earned Rate in the formulas above.

Instructions:

- Review the relevant variance analysis reports to ensure that the driving factor for the variance (Rate/Volume and/or Price/Usage) is addressed at the control account level.  If it is addressed, proceed to Step 2; otherwise, the metric is out of threshold.

- Review the relevant variance analysis reports to ensure that the Rate Variance (RV) formula used is the one specified in Block 6.  If necessary ask the contractor to demonstrate the RV formula used.

- Review the relevant variance analysis reports to ensure that the Volume Variance (VV) formula used is the one specified in Block 6.  If necessary ask the contractor to demonstrate the VV formula used.

- Review the relevant variance analysis reports to ensure that the Price Variance (PV) formula used is the one specified in Block 6.  If necessary, ask the contractor to demonstrate the PV formula used.

- Review the relevant variance analysis reports to ensure that the Usage Variance (UV) formula used is the one specified in Block 6.  If necessary, ask the contractor to demonstrate the UV formula used.

- If all formulas are correctly applied, the metric is within threshold.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/29/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Major change accepted by CCB |  | 02/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update: Test Step and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 7 & 10 | 3/05/2021 |
| v5.0 | Added attribute 23A1 | 4 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |