EVMS Test Metric Specification

Guideline No:

- 23

Test Metric ID:

23A301a

Test Type:

Manual

Attribute/Intent Definition:

23A3:  Schedule variance analysis is supplemented with Integrated Master Schedule (IMS) analysis, and assesses the impact to future tasks/activities on the critical path, near-critical paths, and driving paths.

Test Definition:

Does the Schedule Variance (SV) analysis include documented impact to future tasks/activities & milestones on the critical path, near-critical paths, or driving paths?

Test Metric:

X = Count of sampled CA with reported SV VARs that do not address impact to the critical path, near-critical paths, or driving paths

Y = Total count of sampled CA with reported SV VARs

Metric Threshold:

X/Y ≤ 20%

Data Elements Required:

11 IMS

11AR CA UIDs

11AM Task/Milestone UIDs

12 Program Critical Path

12A Program Critical Path Activities

12B Near-Critical Path Activities

12C Driving Path Activities

16 Internal Variance Analysis Reports

16A VARs

45 IMS Data Dictionary

Assumptions:

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If VARs cannot be directly traced to tasks/activities & milestones in the IMS, consult with the contractor; if after consulting with the contractor the traceability cannot be established, the metric is out of threshold.

Instructions:

- Identify all IMS tasks/activities & milestones that are on the program critical path, near-critical path(s), and driving path(s) (see IPMR CDRL for program, near, and driving path reporting requirements).

- From the list of tasks/activities & milestones identified in step 1, sample a set of CAs with reported SV VARs (e.g., use the Control Account ID to trace from the IMS to the VAR and vice versa); this is the denominator (Y) of the test metric.

- Count each VAR that does not address the impact to critical path, near-critical path(s), or driving path(s).  This is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Major change accepted by CCB |  | 02/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update: Test Metrics, Data Elements Required, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 08/30/2020 |
| v3.6.1 | Added “activities & milestones” in block 6, 11, and 12, with corresponding data element in block 10 |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |