EVMS Test Metric Specification

Guideline No:

- 23

Test Metric ID:

23A401a

Test Type:

Manual

Attribute/Intent Definition:

23A4:  Corrective actions/mitigation plans are identified.

Test Definition:

Do the root cause analysis, impact and corrective action address the variance/issue?

Test Metric:

X = Count of sampled VARs (including root cause, impact, and corrective action) that do not address variance/issue

Y = Total count of sampled VARs

Metric Threshold:

X/Y ≤ 15%

Data Elements Required:

03 EVM System Description

03S VAR Requirements

17 Variance Analysis Reports (VARs)

17D VARs

20 IPMR/CPR/IPMDAR

20U Format 5 VARs/ Performance Narrative Report VARs

46 IPMR/CPR/IPMDAR CDRL

46A VAR Thresholds/Requirements

Assumptions:

- Test metric is based on a sample of VARs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- The EVMSD specifies what constitutes an acceptable root cause analysis, impact statement and corrective action; if the EVMSD does not specify these requirements, this metric is out of threshold.

Instructions:

- Select a sample of VARs to be reviewed; this is the denominator (Y) of the metric.

- Verify that each sampled VAR addresses the following elements as required by contractual direction and the system description:

  - Root cause(s)

  - Impact(s)

  - Corrective action(s)

- Count the number of VARs that do not address each item in Step 2; this is the numerator (X) of the test metric.

- Calculate the Test Metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/29/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Minor change submitted to CCB |  | 02/28/2017 |
| v3.0 | Minor changes accepted by CCB |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 9 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |