EVMS Test Metric Specification

Guideline No:

- 24

Test Metric ID:

24A101a

Test Type:

Manual

Attribute/Intent Definition:

24A1:  Analysis of indirect cost variances, by overhead category, that exceed established thresholds is conducted monthly. Indirect variance analysis includes root cause analysis, impact, and corrective action plans that are tracked through implementation to closure.

Test Definition:

Does indirect variance analysis address root cause, impact, and corrective action?

Test Metric:

X = Count of overhead categories that do not address indirect cost variances when required

Y = Total count of overhead categories that require indirect cost variance analysis

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

15 Internal Variance Analysis Thresholds

15A Internal Variance Analysis Thresholds

17 Variance Analysis Reports (VARs)

17A Indirect VARs

23 CAS Disclosure Statement

23A Indirect Cost Pools

24 FPRA/FPRP

24B Overhead Categories/Departments

Assumptions:

- This metric assumes that the contractor has submitted a Cost Accounting Standards Board (CASB) Disclosure Statement.  For the instances where DCMA has limited access to the contractor’s accounting system data (due to a superseding host nation agreement), then DCMA should instead request/review supporting data from the appropriate organization IAW the host nation agreement.

- Indirect cost variance analysis thresholds are established at the overhead category level or lower (e.g., department level).

Instructions:

- Determine the total number of overhead category levels for the current month that require indirect cost variance analysis; this number is the denominator (Y) of the test metric.

- Review VARs for the current month to determine the number of overhead category levels breaching thresholds that do not address indirect cost variances when required.  Indirect cost variance analysis must address root cause, impact, corrective action/mitigation plans, and potential for indirect rate changes.  Count the number of overhead categories where the required indirect cost variance analysis does not address these elements; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/29/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |