EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A101b

Test Type:

Manual

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly adjusted to reflect program progress, as well as scope and schedule changes. This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Are comprehensive EACs performed according to the standards described in the EVM system description?

Test Metric:

X = Count of contracts with a CEAC not performed according to the EVMSD

Metric Threshold:

X = 0

Data Elements Required:

03 EVM System Description

03W CEAC Process/Requirements

06 Contractual Documents

06A Contracts Requiring EVMS

33 Comprehensive EAC Documentation

33A CEAC Commencement and Completion Dates

Assumptions:

- This test is applied to all contracts included in the EVMS surveillance event data call.

- New contracts less than one year from the start of EVM reporting are exempt from this metric.

Instructions:

- Review the EVM system description to determine the required elements of the CEAC process.

- For each contract with EVMS requirements, determine if the most recent CEAC was performed in accordance with the standards and requirements outlined in the EVM system description (e.g., CEAC documentation contains ground rules and assumptions).  For each CEAC that was not performed in accordance with the EVM system description, count the contract in the test metric (X).

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| NEW | New metric proposed at Feb 2 CCB | All | 03/21/2017 |
| v3.0 | CCB – validated |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Update Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |