EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A102a

Test Type:

Automated

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly to reflect program progress, as well as scope and schedule changes. This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Are time-phased estimates to complete aligned with the remaining tasks in the integrated master schedule?

Test Metric:

X = Count of incomplete WPs/PPs/SLPPs in the EV Cost Tool where time-phased ETC does not align with forecast dates in the IMS

Y = Total count of incomplete WPs/PPs/SLPPs in the EV Cost Tool that are also within the IMS

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting Fiscal Calendar

02B Beginning of period (BOP) dates

02C End of period (EOP) dates

11 Integrated Master Schedule (IMS)

11V Forecast Finish Date

11W Forecast Start Date

11AG Status Date

11AP WP/PP/SLPP UIDs

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AM ETC (Time-phased)

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- EV Cost Tool data forecast start date is determined by the first accounting/fiscal month of non-zero time-phased ETC.

- EV Cost Tool data forecast finish date is determined by the last accounting/fiscal month of non-zero time-phased ETC.

- Forecast start dates are only compared if the IMS forecast start date is after the status date.

Instructions:

- Identify and count all incomplete WPs/PPs/SLPPs in the EV Cost Tool data that are also within the IMS; this is the denominator (Y) of the test metric.

- From the population in step one, compare the EV Cost Tool data forecast start (assumption 2, above) to the forecast start in the IMS. Second, compare the EV Cost Tool data forecast finish (assumption 3, above) to the forecast finish in the IMS. Count each WP/PP/SLPP where the forecast start, forecast finish or both dates do not align; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Updated assumptions, minor changes, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update: Test Type, Test Metric, Data Elements Required, Assumptions, and Instructions |  | 2/22/2020 |
| v3.5.1 | Updated Instructions |  | 4/08/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v3.6.1 | Updated to re-define Y. Updated Assumptions to align with instructions. Updated instructions Step 1 and 2. Admin update to “EV Cost Tool” |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data elements 44 & 45 to supplement artifacts 11 & 13. Updated wording for DECM consistency (WP/PP/SLPP). | 6, 8, 10 | 3/05/2021 |
| v5.0 | Updated WP complete assumption to include LOE and align with other metrics. Updated Data Elements to include 11AG and 13AP. | 8, 9 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |