EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A102b

Test Type:

Manual

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly to reflect program progress, as well as scope and schedule changes. This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Are time-phased estimates to complete aligned with the remaining tasks in the integrated master schedule?

Test Metric:

X = Count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool where time-phased ETC does not align with forecast dates in the IMS

Y = Total count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool that are also within the IMS

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting Fiscal Calendar

02B Beginning of period (BOP) dates

02C End of period (EOP) dates

11 Integrated Master Schedule (IMS)

11AM Task/Milestone UIDs

11AP WP/PP/SLPP UIDs

11V Forecast Finish Date

11W Forecast Start Date

11AG Status Date

11AT IMS ETC (time-phasing) if applicable

13 EV Cost Tool Data

13BA WP/PP/SLPP UIDs

13K BAC for CA and SLPP

13M BAC for WP and PP

13Q BCWPCUM

13AM ETC (Time-phased)

13AP EVT

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- EV Cost Tool data forecast start date is determined by the first accounting/fiscal month of non-zero time-phased ETC.

- EV Cost Tool data forecast finish date is determined by the last accounting/fiscal month of non-zero time-phased ETC.

- Forecast start dates are only compared if the IMS forecast start date is after the status date.

Instructions:

- Identify a sample of incomplete WPs/PPs/SLPPs in the EV Cost Tool data that are also within the IMS; this is the denominator (Y) of the test metric.

- Identify the time-phased ETC in the EV Cost Tool data for the sampled incomplete WPs/PPs/SLPPs.

- Using the sample from Step 1:

  - If associated tasks/activities have ETC time-phasing in the IMS: Compare the Cost Tool data ETC time-phasing to the IMS ETC (time-phasing).

  - If associated tasks/activities do not have ETC time-phasing in the IMS: Compare the Cost Tool data ETC time-phasing to the tasks/activities forecasted in the IMS.

- Count each WP/PP/SLPP where the EV Cost Tool data time-phasing does not align to the IMS time-phasing. Alignment between IMS and Cost Tool data is measured in terms of Period of Performance, gaps in time, front loaded, and back loaded.  This is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v3.6 | New Metric Created |  | 08/30/2020 |
| v3.6.1 | Updated to re-define Y. Updated Assumptions. Updated instructions step 1 and 4 to clarify Test Metric Intent. Admin update to correct capitalization and clarify steps wording |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data elements 44 & 45 to supplement artifacts 11 & 13. Updated WP/PP/SLPP for DECM consistency. | 6, 8,10 | 3/05/2021 |
| v5.0 | Updated WP complete assumption to include LOE and align with other metrics. Updated Data Elements to include 11AG and 13AP. | 8, 9 | 12/13/2021 |
| v6.0 | Corrected Data Element 11AR with new data element 11AT; replaced “resource loaded” with “ETC time-phasing” | 8, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |