EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A104b

Test Type:

Automated

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly adjusted to reflect program progress, as well as scope and schedule changes.  This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Are ETCs generated for completed WPs?

Test Metric:

X = Sum ETC value of completed WPs with ETC

Metric Threshold:

X = 0

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AH EAC

13AL ETC

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- BCWPCUM = BAC, then WP is complete.

Instructions:

- Identify all completed WPs in the EV Cost Tool data with ETC.

- Sum the ETC values for completed WPs; this is (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “from the EV Cost Tool data” in blk 6 & 10 for clarification. Added data element 44 to supplement artifact 13 & updated data elements in blk 8. Added asm 4 blk 9 to differentiate discrete from LOE complete. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | Updated Data Elements to include 13AP | 8 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |