EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A203a

Test Type:

Manual

Attribute/Intent Definition:

27A2:  The direct/indirect rates used for ETCs/EACs consider the latest information available.

Test Definition:

Is the latest information related to direct/indirect rates used for development of ETCs?

Test Metric:

X = Count of sampled incomplete WPs from the EV Cost Tool where direct and indirect rates are not applied correctly to the ETC

Y = Total count of sampled incomplete WPs

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13AL ETC

13AP EVT

13BA WP/PP/SLPP UIDs

13M BAC for WP and PP

13Q BCWPCUM

14 Accounting System Data

14E Direct/Indirect Rates

24 FPRA/FPRP (or published indirect rates)

24A Direct/Indirect Rates

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete WPs.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

Instructions:

- Select a sample of incomplete WPs from the EV Cost Tool data; this is the denominator (Y) of the test metric.

- For each incomplete WP, verify that the rate(s) used to calculate the ETC match the latest company-issued rate set (for forecast purposes).  Count each WP that has a rate that was used to calculate the ETC that does not match the most current published rate; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “from the EV Cost Tool data” in blk 6 & 10 for clarification. Added data element 44 to supplement artifact 13 & updated data elements in blk 8. Added asm 4 blk 9 to differentiate discrete from LOE complete. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | Updated Data Elements to include 13AP | 8 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |