EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27I101a

Test Type:

Automated

Attribute/Intent Definition:

27I1:  ETCs are developed at the work package, planning package, and Summary Level Planning Package (SLPP) levels, or where resources are identified (if lower than the work package level), and are added to the ACWP to calculate the EAC.

Test Definition:

Are ETCs generated for WPs/PPs/SLPPs?

Test Metric:

X = Count of incomplete WPs/PPs/SLPPs with BAC > 0 and ETC ≤ 0

Y = Total count of incomplete WPs/PPs/SLPPs with BAC > 0

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AL ETC

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- Use rounding to the nearest whole number for BAC and ETC (identified in block 6 and block 10: X and Y values).

Instructions:

- Identify and count the total number of incomplete WPs/PPs/SLPPs with BAC > 0; this is the denominator (Y) of the test metric.

- Identify and count the total number of incomplete WPs/PPs/SLPPs with BAC > 0 and ETC ≤ 0; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Major changes accepted by CCB |  | 02/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" in blk 9 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Added Data Element 62; updated to include IPMDAR | 8, 9, 10 | 12/7/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |