EVMS Test Metric Specification

Guideline No:

- 28

Test Metric ID:

28A101a

Test Type:

Manual

Attribute/Intent Definition:

28A1:  Authorized work scope/budget changes are incorporated in the PMB and the Integrated Master Schedule (IMS) as soon as practicable.

Test Definition:

Are authorized work scope/budget changes incorporated into the PMB as soon as practicable?

Test Metric:

X = Count of sampled contract modifications that were not incorporated into the PMB in a timely manner in accordance with the system description

Y = Total count of sampled contract modifications

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

03 EVM System Description

03J PMB Incorporation Timeframe

06 Contractual Documents

06G Contractual Mods (Authorization Dates)

06H Contractual Mods Adding/Removing Scope

18 Baseline Control Logs

18G Date of Contractual Mod Incorporation into PMB

Assumptions:

- For the purpose of this metric, only contract modifications that add, remove, or revise work scope are considered.

- Test metric is based on a sample of contractual modifications executed within the most recent 12 months of transactions (but excluding the accounting periods allowed by the EVM SD for UB distribution, or the previous two accounting periods if not specified by the EVM SD).

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Review the system description to determine how timely incorporation of contractual changes is defined.

- Identify a sample of contract modifications authorized during the last year that add, remove or revise work scope; this is the denominator (Y) of the test metric. (Note: Exclude the accounting periods allowed by the EVM SD for UB distribution; if this is not specified in the SD, exclude the previous two accounting periods).

- Compare the authorization date of each sampled contract modification in Step 2 to the incorporation date in the baseline control log.  Count any contract modification that is not incorporated into the PMB (Control Accounts and SLPPs and residual UB in MR) in accordance with the system description; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Revised instruction language to be consistent with assumption & global assumption (#2) |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |