EVMS Test Metric Specification

Guideline No:

- 28

Test Metric ID:

28A201a

Test Type:

Manual

Attribute/Intent Definition:

28A2:  UB is distributed to or removed from control accounts or SLPPs as quickly as practicable.

Test Definition:

Is UB distributed in a timely manner?

Test Metric:

X = Dollar value of UB samples not distributed within the timeframe specified in the SD

Y = Total UB dollar value of sampled contract mods or baseline change requests

Metric Threshold:

X/Y = 0%

Data Elements Required:

03 EVM System Description

03N UB Distribution Timeframe

18 Baseline Control Logs

18K UB

18L UB Distributions

Assumptions:

- Test metric is based on a sample of UB not distributed within the timeframe specified in the EVM SD.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Authorization to proceed on scope of work held in UB has been provided by the customer.

Instructions:

- Sample contract mods or baseline change requests that create UB, and sum the UB value of the samples; this is the denominator (Y) of the metric. Disregard any contract mods or baseline change requests that created the UB sample if the full UB would not be able to be distributed by the date of CPR/IPMR report date.  (e.g., UB must be distributed within 90 days but the UB sample was only created the previous reporting period.  Do not use this sample as per the system description the contractor would still have another two reporting periods before this UB would need to be planned.)

- For these samples, identify and calculate the dollar value of UB not distributed within the timeframe specified in the system description; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detail Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Approval (Original) | All | 9/14/2015 |
| v2.0 | CCB - validated |  | 8/16/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| RED | Major change accepted by CCB |  | 2/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |